## Timeclocks
Date	In	Out	Hours		In	Out	Hours	Total		Notes	818:49
12/07/21	08:15 AM	01:44 PM	05:29		02:57 PM	05:35 PM	02:37	08:07		VR investigation, Unity project, design document, avatar, control scripts
12/8/21 (Immaculate Conception)	08:07 AM	12:00 PM	03:52				00:00	03:52		Avatar cleanup, animations import, script/prefab consolidations, formatting cleanups, doors, room controller & spawning
12/09/21	08:12 AM	12:53 PM	04:41		02:03 PM	05:20 PM	03:17	07:58		Camera follow, items, bounciness, pick-up/drop, PlayerController inheritance cleanup; recruiter chat
12/10/21	08:12 AM	01:41 PM	05:28		02:43 PM	05:33 PM	02:49	08:18		PlayerController cleanup, knife sprite, item aim/swing, getter simplifications, fast item damage, enemies
			00:00				00:00	00:00			28:16
12/13/21	08:09 AM	12:23 PM	04:13		01:19 PM	05:34 PM	04:15	08:28		Enemy cleanup, object tags, death item drop, character combined animation logic, continual death prevention, player→avatar rename, thrown items & improved swing, focus indicator, wall cling
12/14/21	08:01 AM	01:01 PM	04:59		02:04 PM	05:04 PM	03:00	07:59		Wall cling/jump, Simulation class cleanup, multi-hit health, strafing, encapsulated event logic, health UI
12/15/21	08:10 AM	12:50 PM	04:39		01:53 PM	04:29 PM	02:35	07:15		2D room spawning, one-way platforms, room spawn fix, tables
12/16/21	08:03 AM	11:59 AM	03:55		01:07 PM	05:17 PM	04:09	08:04		Tables cleanup, script tags, aim-based camera follow, improved secondary item positioning, enemy waves & wave timer, victory zone
12/17/21	08:00 AM	11:58 AM	03:57		01:00 PM	05:10 PM	04:09	08:07		Post-damage invincibility, near ground wall movement improvement, victory zone placement, GameController coroutines, GitHub backup, URP, table width fix, Unity update, lighting!
			00:00				00:00	00:00			39:55
12/20/21	08:10 AM	12:44 PM	04:34		01:52 PM	05:04 PM	03:11	07:46		Pause & pause menu, game over menu & events cleanup, shadows manual shapes, item/camera aim jitter fix & out-of-bounds detection, health missing indicators
12/21/21	08:10 AM	12:27 PM	04:17		03:22 PM	06:42 PM	03:20	07:37		Health missing cleanup, respawn/win movement fixes, audio placeholders, more asset tags, item swing trails
12/22/21 (travel)			00:00				00:00	00:00
12/23/21 (Christmas Eve Eve)			00:00				00:00	00:00
12/24/21 (Christmas Eve)			00:00				00:00	00:00
			00:00				00:00	00:00			15:23
12/27/21 (Christmas)			00:00				00:00	00:00
12/28/21 (Christmas)			00:00				00:00	00:00
12/29/21 (Christmas)			00:00				00:00	00:00
12/30/21 (Christmas)			00:00				00:00	00:00
12/31/21 (New Year’s Eve)			00:00				00:00	00:00
			00:00				00:00	00:00			00:00
1/10/2022 (travel)			00:00				00:00	00:00
01/11/22	08:05 AM	10:13 AM	02:08		11:13 AM	05:21 PM	06:08	08:16		Timesheet reformat, newline consistency fix, inventory click handling, WIP guidance, victory w/ enemies tweak, swing trail fade out & fixes & improvements
01/12/22	08:00 AM	12:34 PM	04:34		01:41 PM	05:05 PM	03:24	07:59		Swing trail cleanup, WeightedObject, AI state machines! spawn/respawn improvements
01/13/22	08:08 AM	01:01 PM	04:52		02:06 PM	05:33 PM	03:27	08:19		AIState improvements, “bats” and simple flight movement, bat swoop attacks, Item base prefab
01/14/22	08:21 AM	01:13 PM	04:52		02:13 PM	04:55 PM	02:41	07:33		Color improvements, bat fly/death sprites/animations, pathfinding!
			00:00				00:00	00:00			32:09
1/17/22 (MLK Day)			00:00				00:00	00:00
01/18/22	08:03 AM	12:23 PM	04:20		01:25 PM	05:01 PM	03:35	07:56		Pathfinding cleanup, VS IntelliSense suggestions, AI debug, wave escalation, enemy spawn debug, AIMelee continual swings, shadow item fix, enemy collision fixes
01/19/22	08:16 AM	04:20 PM	08:03				00:00	08:03		Inventory/item/damage tweaks, pathfind through walls prevention, aim trail VFX, camera aim tweaks
01/20/22	08:01 AM	11:44 AM	03:43		12:51 PM	05:12 PM	04:20	08:03		Item variable damage, enemy non-lethal damage movement, collision disable/enable helper, damage movement tweak, enemy rename, arms
01/21/22	08:06 AM	12:18 PM	04:12		01:28 PM	05:14 PM	03:45	07:57		Arms cleanup, item aim/swing differentiation
			00:00				00:00	00:00			32:01
01/24/22	08:07 AM	11:52 AM	03:44		01:05 PM	05:11 PM	04:06	07:50		Arms cleanup, key-in-hand unlock fix, arm animated attachment offsets, dialogue UI & DialogueController
01/25/22	08:01 AM	12:54 PM	04:53		01:56 PM	05:05 PM	03:08	08:02		Control disable/enable and item fixes, namespace removal, backpacks!
01/26/22	07:58 AM	12:07 PM	04:08		01:08 PM	05:29 PM	04:20	08:28		Backpack cleanup, base attachable prefab, AnimationController→KinematicCharacter, backpack auto-retrieval, backpack variation & animated offsets
01/27/22	08:25 AM	12:11 PM	03:45		12:57 PM	05:30 PM	04:33	08:19		Bat attack/hurt SFX & animations, item/backpack separation, pack detached collision fix, IHolder rename, throw cancellation & focus fixes, spears & item multi-collider handling
01/28/22	08:10 AM	12:16 PM	04:05		01:51 PM	04:53 PM	03:01	07:07		NeverDie console command, parchments & screen overlay text & combination keys, door interaction & combination locks!
			00:00				00:00	00:00			39:48
01/31/22	08:10 AM	01:46 PM	05:36		02:47 PM	05:21 PM	02:33	08:10		GameController.Instance, room size variation, boss fight (boss room & spawning, BossRoom.cs)!
02/01/22	08:05 AM	12:31 PM	04:26		01:35 PM	04:53 PM	03:18	07:45		Boss fight cleanup, backpack death drop, inventory refresh reliability, overlay movement prevention, invisible locks fix, combination UI improvements
02/02/22	08:07 AM	01:23 PM	05:15		02:33 PM	05:32 PM	02:59	08:15		Item damage-disable fix, table item spawn fixes, combination UI despawn fix, focus interact priority & button prompt, game reload, death/victory helper, key cleanup consistency, items in backpacks fixes
02/03/22	08:15 AM	11:32 AM	03:16		12:34 PM	04:56 PM	04:22	07:38		Items in backpacks cleanup, inventory refresh after swap, avatar prefab, boss room ladder fix, wall cling improvements, wall jump velocity blending fixes, aim/table stale visibility fixes, flashlights!
02/04/22	08:16 AM	12:41 PM	04:24		01:54 PM	05:21 PM	03:27	07:52		Arm multi-point aim! Inventory drag’n-drop fix & menu-based drop, vertical room fixes, game save & clear, gamepad support!
			00:00				00:00	00:00			39:42
2/07/22 (bday)			00:00				00:00	00:00
02/08/22	08:05 AM	12:05 PM	03:59		01:15 PM	05:19 PM	04:04	08:04		Gamepad support cleanup, InputSystem migration
02/09/22	08:03 AM	03:57 PM	07:54				00:00	07:54		Input debug visualizations, menu button navigation, room generic connections & un-biased directions
02/10/22	08:19 AM	12:20 PM	04:00		01:30 PM	05:25 PM	03:55	07:56		LayoutGenerator, room spawning / locks / items / boss room via LayoutGenerator
02/11/22	08:16 AM	12:47 PM	04:31		01:52 PM	05:14 PM	03:21	07:53		Items / boss room via LayoutGenerator cleanup, combo lock input fix, keys via LayoutGenerator, room layout debug display, secret/breakable doors, gate placement improvement
			00:00				00:00	00:00			31:48
02/14/22	08:17 AM	11:34 AM	03:16		12:40 PM	05:33 PM	04:53	08:10		Lock placement cleanup, item throw collision fix, interface to component simplification, ConsoleCommand efficiency, enemies spawning behind locks fix, avatar multi-instance prep, local co-op!
02/15/22	08:02 AM	01:21 PM	05:18		02:22 PM	04:54 PM	02:32	07:50		Co-op cleanup, co-op overlays fix, erroneous warnings suppressions, co-op mouse aim & inventory fixes, arm swinging
02/16/22	08:20 AM	04:41 PM	08:21				00:00	08:21		Wall jump normals improvements/fixes, co-op enemy on-death target switch, room/layout double-spawn assert fix, friendly fire prevention, multi-avatar lighting fix, co-op focus visibility & backpack inventory fixes
02/17/22	08:13 AM	12:44 PM	04:31		01:45 PM	05:04 PM	03:19	07:51		Door/key variety, item small fixes, UI partial HP display, health tweaks, door combination variety, remote doors/locks
02/18/22	08:12 AM	12:16 PM	04:03		01:28 PM	05:37 PM	04:08	08:12		Remote doors/locks cleanup, boss lock multi-keying! console correct placement, spawn positions fix, MaybeReplaceDoor() loop simplification
			00:00				00:00	00:00			40:27
2/21/22 (Presidents’ Day)			00:00				00:00	00:00
02/22/22	08:03 AM	01:35 PM	05:31		02:36 PM	05:19 PM	02:43	08:14		Room size & movement speed decreases, audio/attachment fixes, Ableton investigation
02/23/22	08:09 AM	01:17 PM	05:07		01:39 PM	04:56 PM	03:16	08:24		Player input routing improvements, material system! arm collider caching, inventory control loss fixes, material variety
02/24/22	08:16 AM	01:34 PM	05:18		02:40 PM	05:16 PM	02:35	07:53		Combination lock submit fix, pathfinding reliability improvement, breakability indications, inventory controls expansion & highlighting, inventory missing backpack slot fix, boss intro improvements
02/25/22	08:12 AM	01:21 PM	05:09		02:33 PM	05:18 PM	02:45	07:54		Boss intro audio & cleanup, ladder centering/spawning/variation, gate unlock camera grab, enemy periodic replanning, settings update / debug build
			00:00				00:00	00:00			32:27
02/28/22	08:10 AM	01:28 PM	05:18		02:35 PM	05:34 PM	02:58	08:17		Console commands in build fix, gamepad stick improvements, UnlockAll, co-op shared camera, avatar movement spring, boss room pathfinding fix
03/01/22	07:58 AM	12:27 PM	04:29		01:29 PM	03:15 PM	01:45	06:15		Pathfinding fix cleanup, size normalizations, landmarks
03/02/22	08:16 AM	12:17 PM	04:01		01:13 PM	05:06 PM	03:53	07:54		Landmarks cleanup, boss distances fixes, prefab directory cleanup, light flickering, room placement fix
03/03/22	08:07 AM	01:11 PM	05:04		02:12 PM	05:57 PM	03:44	08:49		Room placement fix cleanup, floor item loss prevention, layout difficulty curve, layout colored areas & variety, avatar health bump, enemy spawn collision prevention, AI swoop & stuck controls fixes
3/4/22 (V visit)	08:21 AM	11:47 AM	03:25				00:00	03:25		Playtest fixes/improvements, build/backup
			00:00				00:00	00:00			34:42
3/7/22 (V visit)			00:00				00:00	00:00
03/08/22	08:02 AM	11:38 AM	03:36		01:10 PM	05:26 PM	04:16	07:52		Overlay controls improvement, backpack item retrieval fix, co-op inventory UI fix, multi-node rooms, “rare” items, shelves & books, miscellaneous tweaks
03/09/22	08:13 AM	11:35 AM	03:21		12:42 PM	05:36 PM	04:53	08:15		Enemy controlled ladder descent, “uncolored” focus, arm/item damage improvements, enemy movement SFX, enemy spawn points & time-distributed waves
03/10/22	08:17 AM	01:07 PM	04:50		02:12 PM	05:27 PM	03:14	08:05		Room bounds efficiency, multi-backpack inventory fixes, locked-room waves, physics overlap prevention/workarounds, flashlight damage fix
03/11/22	08:06 AM	12:54 PM	04:48		01:58 PM	05:24 PM	03:26	08:14		Overlap/damage/miscellaneous cleanup, item color removal, in-world/inventory text & static combination keys, button-based locks, more sprite/prefab tagging
			00:00				00:00	00:00			32:27
03/14/22	08:05 AM	01:10 PM	05:05		02:08 PM	05:05 PM	02:57	08:02		Layout earlier lock placement & tighter grouping!
03/15/22	08:03 AM	09:54 AM	01:51		11:10 AM	05:01 PM	05:51	07:42		Bug bombs! Bug bomb SFX, key unreachability prevention, text in-world / lock destroy assert fixes, multi-controller support
03/16/22	08:23 AM	11:45 AM	03:22		12:51 PM	05:19 PM	04:27	07:50		Computer de-dust, multi-controller cleanup, dialogue text fix, button prompt generalization, room direction-based gates, ladder gates
03/17/22	08:15 AM	11:59 AM	03:43		01:23 PM	05:23 PM	04:00	07:43		Co-op unreachable enemy cleanup, avatar jump fix, colors improvements, stale swing info fix, swing info upgrades
03/18/22	08:04 AM	12:50 PM	04:46		01:53 PM	05:29 PM	03:36	08:22		Item mass tweaks, swords, item rest offsets, differential swing input, more tagging, entryway scene, IsSwinging heavy item improvement
			00:00				00:00	00:00			39:42
03/21/22	08:19 AM	01:04 PM	04:45		02:06 PM	05:24 PM	03:17	08:03		Attachable interface, stormy windows, boss spawning
03/22/22	08:06 AM	10:55 AM	02:49		12:00 PM	05:19 PM	05:19	08:09		SFX for flashlights / lightning / menu buttons, GameController.Instance fix, NPC w/ dialogue, layout conciseness improvements
03/23/22	08:13 AM	04:09 PM	07:56				00:00	07:56		Generation retry slight decrease, room types, spear fix, room backdrops by type, room shadow improvement, room wall simplification, item color limits
03/24/22	08:11 AM	09:41 AM	01:30		10:40 AM	05:07 PM	06:26	07:56		Dialogue portraits, gate/door shadow fixes! Entryway expansion!
3/25/22 (Annunciation)			00:00				00:00	00:00
			00:00				00:00	00:00			32:05
03/28/22	08:13 AM	01:14 PM	05:00		02:20 PM	05:36 PM	03:16	08:17		Game over in entryway, room doorway count increase, arm connections, inter-level progress! item trail improvement
03/29/22	08:11 AM	11:33 AM	03:22		12:25 PM	05:11 PM	04:46	08:08		Item trail cleanup, aim trail instant update, “skeletons”! dropped item persistence fix
03/30/22	08:14 AM	11:35 AM	03:20		11:55 AM	04:39 PM	04:44	08:04		Utility functions as extensions, doorway clear fix, color randomization improvements, inventory/control small fixes, boss music fixes, door seal VFX
03/31/22	08:01 AM	01:10 PM	05:08		02:10 PM	06:20 PM	04:09	09:18		Ladder rope physics, ladder rope display
04/01/22	08:01 AM	01:31 PM	05:30		02:37 PM	04:19 PM	01:41	07:11		Ladder rope display cleanup, key ordering & Simon Says puzzles, ladder spawn improvements, layer/audio cleanup
			00:00				00:00	00:00			41:00
04/04/22	08:29 AM	11:41 AM	03:12		12:35 PM	05:52 PM	05:17	08:29		Layer/audio cleanup, room object overlap prevention, sorting layers, Locks/ w/i Rooms/, furniture spawn simplification, layout hidden bonuses
04/05/22	08:07 AM	10:14 AM	02:06		11:26 AM	05:19 PM	05:52	07:59		Layout hidden bonuses cleanup, Entryway misc. fixes, boss teleport! GateDust despawn
04/06/22	08:07 AM	04:02 PM	07:54				00:00	07:54		Boss teleport cleanup, item tooltips! Inventory gamepad/key navigation, Entryway contents saving
04/07/22	08:08 AM	11:50 AM	03:42		01:02 PM	05:27 PM	04:25	08:07		Entryway contents persistence prep/cleanup, Save{Writer/Reader} abstraction for plaintext debug saves
04/08/22	08:25 AM	12:21 PM	03:56		01:52 PM	06:09 PM	04:16	08:13		Save abstraction cleanup/fixes, NPC dialogue expansion & fix, save positions relative to rooms, room doorway refactor, cutbacks WIP
			00:00				00:00	00:00			40:44
4/11/22 (consulting)			00:00				00:00	00:00
4/12/22 (consulting)			00:00				00:00	00:00
4/13/22 (consulting)			00:00				00:00	00:00
4/14/22 (consulting)			00:00				00:00	00:00
4/15/22 (Good Friday)			00:00				00:00	00:00
			00:00				00:00	00:00			00:00
4/18/22 (consulting)			00:00				00:00	00:00
4/19/22 (consulting)			00:00				00:00	00:00
4/20/22 (consulting)			00:00				00:00	00:00
4/21/22 (consulting)			00:00				00:00	00:00
4/22/22 (consulting)			00:00				00:00	00:00
			00:00				00:00	00:00			00:00
04/25/22	09:00 AM	12:50 PM	03:50		01:58 PM	06:43 PM	04:45	08:35		Playtest fixes/improvements: flashlight radius, co-op respawn positions fix, aim/look separation, co-op add/remove player fixes, gamepad aim fix, explosion improvements
4/26/22 (consulting)			00:00				00:00	00:00
4/27/22 (consulting)			00:00				00:00	00:00
4/28/22 (travel)			00:00				00:00	00:00
04/29/22	08:00 AM	12:56 PM	04:56		01:42 PM	05:42 PM	04:00	08:56		Transfer/backup, avatar interact/aim playtest improvements, damage source & existing collisions fixes, dialogue controls fix, tutorial area! Timer warning SFX
			00:00				00:00	00:00			17:32
05/02/22	08:19 AM	12:24 PM	04:05		01:26 PM	05:25 PM	03:58	08:04		Tutorial / timer warning cleanups, spawn position helper/fixes, lock/key refactor
05/03/22	08:08 AM	11:37 AM	03:29		12:50 PM	05:27 PM	04:37	08:06		Component duplication prevention, combination in-world locks, exploration music! tutorial message improvements, multi-collider damage fixes
05/04/22	08:00 AM	10:49 AM	02:49		11:36 AM	05:08 PM	05:32	08:21		AI lockup & “invincibility” fixes cleanup, room contents overlap fixes, dialog ordering/variety, script file organization, puzzle locks!
05/05/22	08:12 AM	12:51 PM	04:39		02:02 PM	05:10 PM	03:08	07:47		Puzzle lock rotation, puzzle lock via masking, lock/key selection improvements
05/06/22	08:06 AM	01:21 PM	05:15				00:00	05:15		Lock/key selection cleanup, music echo / animation pop fixes, door sprite display tweaks, physics push-through-walls prevention,
			00:00				00:00	00:00			37:35
05/09/22	08:11 AM	12:58 PM	04:46		02:03 PM	05:32 PM	03:28	08:15		Post-boss door, entryway further doors, torch VFX
05/10/22	08:12 AM	01:08 PM	04:55		02:12 PM	05:22 PM	03:10	08:06		Lookouts! avatar extreme bunny hop fix, LayerMaskHelper, Utility.OriginToCenterY() improvement
05/11/22	08:19 AM	01:07 PM	04:48		02:05 PM	05:09 PM	03:03	07:52		Cut-backs fix-ups! ladder pass-through improvement, boss teleport VFX & timing, enemy in-flight collision fix
05/12/22	08:08 AM	01:26 PM	05:18		02:26 PM	05:55 PM	03:28	08:47		Room outdoor attempt, snakes! damage bounce verticality fix
05/13/22	08:11 AM	01:39 PM	05:27		02:39 PM	03:25 PM	00:46	06:13		Join/texture tweaks, normal mapping test & avatars, electric hazard locks
			00:00				00:00	00:00			39:15
05/16/22	08:08 AM	01:01 PM	04:52		02:04 PM	05:35 PM	03:30	08:22		Electric hazard locks cleanup, NpcDialogue / NPC types
05/17/22	08:02 AM	12:09 PM	04:06		01:11 PM	05:25 PM	04:14	08:21		NPC type cleanup, InteractSimple split, non-avatar arm improvements, NPC “rescue”, tutorial order fix, key spawning on furniture, UI button prompt sprites
05/18/22	08:05 AM	12:05 PM	04:00		01:11 PM	04:56 PM	03:45	07:45		UI button prompt sprites cleanup, tutorial button prompt conversions, tutorial overlap prevention, save file corruption prevention/fix, frying pans! Item offsets, material fallbacks
05/19/22	08:11 AM	01:44 PM	05:33		02:46 PM	05:01 PM	02:15	07:48		InteriorPosition() bounds assert fix, throw tweaks, markers & drawing! cutback softlock prevention, music “echo” fix
05/20/22	08:11 AM	12:37 PM	04:25		01:46 PM	04:41 PM	02:54	07:20		Cutback/music fixes cleanup, audio/item fixes, improved electricity SFX, sorting layer Architecture split, plastic SFX, character physics improvements, assert fixes
			00:00				00:00	00:00			39:38
05/23/22	08:07 AM	12:10 PM	04:02		01:15 PM	05:12 PM	03:57	08:00		Health gradients, smudge sprite, scene progression! save/physics/focus fixes
05/24/22	08:05 AM	12:20 PM	04:15		01:22 PM	05:31 PM	04:08	08:24		Save fixes cleanup, boss tracking, per-scene escalation, NPC collision workaround, NPC randomization & persistence, marker line fix & draw input improvement
5/25/22 (L ER)			00:00				00:00	00:00
05/26/22	08:12 AM	01:08 PM	04:56		02:10 PM	05:19 PM	03:08	08:05		Wall texture variety, render depth fixes, interaction two-way toggles
05/27/22	08:12 AM	01:13 PM	05:01		02:41 PM	05:35 PM	02:54	07:56		Dialogue replies, dialogue reply cleanup & events
			00:00				00:00	00:00			32:25
5/30/22 (Memorial Day)			00:00				00:00	00:00
05/31/22	08:31 AM	12:52 PM	04:20		01:56 PM	05:26 PM	03:29	07:49		Dialogue replies/events cleanup, DialogueController simplifications, room contents overlap fix, conditional replies, enemy info dialogues
06/01/22	08:18 AM	01:20 PM	05:01		02:30 PM	04:55 PM	02:24	07:26		Dialogue looping, sprite organization, door entry animation, avatar entrance/exit animations
06/02/22	08:09 AM	01:44 PM	05:34		02:49 PM	05:38 PM	02:48	08:23		Zone further differentiation, combination lock sprites, statue puzzles
06/03/22	08:07 AM	01:21 PM	05:13		02:24 PM	05:20 PM	02:56	08:10		Toggle SFX, music additions, attachment alpha mirroring, pixel art investigation
			00:00				00:00	00:00			31:51
06/06/22	08:05 AM	12:18 PM	04:13		01:25 PM	05:13 PM	03:48	08:02		Load array fixes, lock combination multi-character options, combination flavor text, assert messages, room furniture fill percentage
06/07/22	08:09 AM	12:21 PM	04:11		01:25 PM	05:19 PM	03:54	08:06		Room fill/overlap improvements, tutorial re-entry, spawn/despawn animation fixes, beds, generic ladder/capacitor keys, aligned ladder bases
06/08/22	08:12 AM	01:19 PM	05:07		02:33 PM	04:33 PM	01:59	07:07		Generic keys / aligned locks fixes/cleanup, despawn effects for capacitors/bones, AI parabolic aim
06/09/22	07:59 AM	11:58 AM	03:58		01:05 PM	05:37 PM	04:32	08:30		AI parabolic aim cleanup, tutorial optional/advanced room, throwing through furniture/platforms, co-op join during game over prevention, debug reset fixes, spiders
06/10/22	08:12 AM	11:59 AM	03:46		01:18 PM	05:17 PM	03:58	07:45		Spiders cleanup, loading screen & load improvements, room edge shadow improvement, room type preconditions & cellars!
			00:00				00:00	00:00			39:32
06/13/22	07:59 AM	01:07 PM	05:07		02:10 PM	05:05 PM	02:55	08:03		Precondition/cellar cleanup, bedroom dead-end preference, cellar vats, wine bottles & racks
06/14/22	08:10 AM	12:15 PM	04:05		01:04 PM	04:58 PM	03:53	07:59		Glass SFX/VFX, cobwebs & decoration spawn variety, color proportionality, mousetraps! tutorial additions & custom fonts, lit tutorial text investigation
06/15/22	08:16 AM	12:30 PM	04:14		01:41 PM	05:09 PM	03:27	07:42		NPC merchant functionality, cellar rubbish, room decoration height fixes, documentation update, fireplaces
06/16/22	08:24 AM	12:55 PM	04:30				00:00	04:30		Fireplace normals & cleanup, flashlight & item damage fixes, normal map normalization script,
			00:00				00:00	00:00
			00:00				00:00	00:00			28:15
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00			00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00			00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00			00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00
			00:00				00:00	00:00			00:00

## Time Off
12/2021 – 11/2022
12/22/21	Christmas/travel
12/23/22	Christmas travel
01/10/22	Christmas travel
03/04/22	V visit
03/07/22	V visit
04/28/22	Easter travel
05/25/22	L ER